## Slide 1: Tech Dev NewCo - LAUNCH timeline (soft launch 2022)
29 Aug | 5 Sept | 12 Sept | 19 Sept | 26 Sept | 3 Oct | 10 Oct | 17 Oct | 24 Oct | 31 Oct | 7 Nov | 14 Nov | 21 Nov (Thanksgiving) | 28 Nov | 5 Dec | 12 Dec
Sergio Time: 4 hrs | 4 hours | 4 hours | 4 hours | 4 hours | 8 Hours | 8 Hours | 8 Hours | 8 Hours | 8 Hours | 8 Hours | 8 Hours | 8 Hours | 8 Hours | 8 Hours | 8 Hours
Brand Services Found
Marketing Services The Launch Box
Strategic Advisory The Launch Box
Brand Discovery & Definition
Website & Social Media Setup
Marketing Planning
Launch Activities
TLB: Launch Timeline
TLB: Initial Identity Discovery and MVV Development
Found: Brand Identity & Visual Design
Found: Website Architecture & Content Advisory
TLB: Naming Exercise and Legal Name Checks
TLB: Social Media Strategy & Process, Templates
LinkedIn Page LAUNCH TLB – Dec 2
TLB: LI Page SetUp
TLB + Sergio: Create Web Content for Splash Page
TLB: Create Web Content for Full Site
Found: Splash Page Dev
Splash Page LAUNCH Found – Dec 2
TLB: Marketing Plan, Strategy, Function & Budget Development, Calendar, Buyer Personas, Buyer’s Journey
TLB: Content Marketing Strategy Development
TLB: HubSpot Sign Up & Setup
TLB: ZoomInfo Target List Building
Found: Marketing / BD / Deliverable Templates, Graphic Standards
TLB: Advise/Assist/Review On Visual Design, Website, Marketing / BD / Deliverable Templates
TBD: Article/Content Development
TLB: Efforts to Grow LI Followers
Found: Full Website Dev
TLB: Initial Campaign Planning
TLB: Teaser messages?
TLB: Social posts
TLB: Direct Outreach & Intros
TLB: Personal LI Page Messaging

## Slide 2: Tech Dev NewCo - LAUNCH timeline (FULL launch 2023)
19 Dec (partial holiday) | 26 Dec (Holiday Week) | 2 Jan (partial holiday) | 9 Jan | 16 Jan | 23 Jan | 30 Jan | 6 Feb | 13 Feb | 20 Feb | 27 Feb | 6 Mar | 13 Mar | 20 Mar | 27 Mar
Sergio Time: 4 hrs | 0 hours | 4 hours | 8 hours | 8 hours | 8 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours
Brand Services Found
Marketing Services The Launch Box
Strategic Advisory The Launch Box
Brand Discovery & Definition
Website & Social Media
Marketing Planning
Launch Activities
TLB: Continue Creation of Web Content for Full Site
TBD: Continue Article/Content Development
TLB: Continued Efforts to Grow LI Followers
Found: Full Website Dev
Full Site LAUNCH Found – Jan 27
TLB: Continued Campaign Planning
TLB: PR/Announcement Asset Development
Official Launch with PR, media outreach start TLB – Feb 1
TLB: Mission Matters Podcast Development
TLB: Media/Influencer List
TLB: Media Outreach
TLB: Campaigns Launch and Continue thru Q1