## Slide 1: Hyperscayle LAUNCH timeline
18 April | 25 April | 2 May | 9 May | 16 May | 23 May | 30 May (Amy Out) | 6 June (Found Out) | 13 June | 20 June | 27 June | 4 July | 11 July
TLB: Social Media Strategy & Process, Templates
Found: Brand Identity & Visual Design
TLB: PR/Announcement Asset Development
TLB: Advisory/Collaboration On Identity Development, Visual Identity, Web Architecture, Web Development
Brand Services Found
Marketing Services The Launch Box
Strategic Advisory The Launch Box
Found: Identity Discovery and Definition
Found: Marketing / BD / Deliverable Templates, Graphic Standards
Found: Website Architecture & Content Advisory
TLB: Advise/Assist/Review On Marketing / BD / Deliverable Templates
Website LAUNCH Found – Jun 30
PR, Social Launch, Podcast Launch TLB – July 12
TLB: Mission Matters Podcast Development
TLB: Media/Influencer List
Team Kick Off Date TBD
TLB: Marketing Plan, Strategy, Function & Budget Development, Calendar, Buyer Personas, Buyer’s Journey
TLB: Content Marketing Strategy Development
Brand Discovery & Definition
Assets & Content
Marketing Planning
Launch Activities
TLB: LI Refresh
Found: Website Development & Implementation
TLB: Advisory On Content Development (Internal? Outside writer? Intern?)
TLB: Content Support for Developing Use Cases, Service Line Language, Website Content
TLB: Partner Marketing Strategy Development
TLB: HubSpot Sign Up & Setup
TLB: ZoomInfo Target List Building
TLB: Initial Campaign Planning
TLB: MVV Development
TLB: Efforts to Grow LI Followers
Notes: HubSpot – CRM Hub Pro, Marketing Hub Starter – consider if we need an upgrade possibly in fall
Marketing resources – Nick will be main point person, others as they can – we can use part of a TLB intern coming on in July and will consider a Hyperscayle intern in the fall
Kick off or Launch event – need to discuss

## Slide 2: Hyperscayle 2022 business objectives & Marketing Strategy
FIRM Business Objectives​ What are the agreed-upon, prioritized business objectives that map to marketing program objectives & goals for this year?​ | Marketing Strategy​ What do you plan to do? How do marketing plans and activities address the business strategy? ​ | Program Objectives & Key Measures​ What are the program objectives you plan to focus on, and key measures you & your team will use to measure performance?​
Complete launch of website, brand assets, social media presence ​ | Develop marketing strategy, budget, calendar for 6 months Full site launch, social media refresh, PR and formal “launch” Branded templates​ and materials for brand ownership Complete all required supporting assets for BD, deliverables (review 3 mos)​ Optimize website for hiring/attracting more talent | Baseline of website visitors/month to establish targets ​ Baseline of social followers to establish targets​ 1-2 posts/week on LinkedIn ​ # Inbound leads​
Revenue goal - $2M annual revenue goal Net New Marketing Target Gen - $100k (5-8 opps) pipeline | Persona and buyer’s journey development List building Launch targeted campaigns Focus on top of funnel/pipeline | # net new marketing-sourced opportunities $ marketing-generated pipeline
Maximize the value of investments in partner programs (Double down with OpenPrise, GreatHill Partners (PE)) | Assist with definition of overall partner strategy Create announcements (PR & social) on all new partnerships Add partner list to website Execute at least one event or initiative with each partner Content and case studies Cross-promotion of partner assets (they share ours / we share theirs) | # of contacts added to HubSpot # of leads passed for BD $ marketing-generated pipeline Partner awards?
Establish awareness of Hyperscayle in PE (add another PE firm?) | Messaging, personas | 
Develop and promote specific offering (Diligence package for PE, Marketing Foundation package) | Develop market-facing website & collaterals Create articles and assets to support inbound, including animated videos Influencer development, media & influencer list Proactive media outreach, proactive industry analyst briefings (Gartner, etc.) Outbound campaigns TBD | Inbound leads #MQLs passed to team Marketing generated pipeline
Maintain pride in culture as we scale, while promoting personal brands | Embed culture and messaging into HR processes (recruiting, onboarding) Values-based people posts – videos? Award applications Proactively ID media and speaking opportunities for broader team Optimize website for hiring/attracting more talent | Employee feedback on HR process MAINTAIN LI post engagement of 5% on people posts # awards won # of speaking/article placements
Aggressively grow “owned” audience, including contacts in HubSpot | Grow social media followers and convert LinkedIn connections to followers Newsletter w subscribers? Leverage website forms and creative offers Participate in events, webinars, etc. that result in lists  HubSpot Install a HubSpot chat bot/popups on site to gather basic info | % growth in # followers % growth in # subscribers # of contacts added to HubSpot # of leads passed for BD $ marketing-generated pipeline
Notes: B2B SaaS as a focus industry? Both Nick and Tony have strong experience here and can tell good stories
Tony – mid level, Nick –c-level/VC/PE (solution engineer style), Ben – VC/PE (sales style)
Double down on equity side
Marketing goal per Ben - 100k close (4 opportunities – 1-2 close)
Marketing goal per Nick - $100k pipeline (5-8 opps)
2023 – Target rev $3M
Marketing should contribute 400-600k (about 20%)
Which means 1-1.2M in pipe
Since each deal averages $50k this means 20-24 marketing sourced deals in the pipe
Targeting – need to prioritize
Growth Equity
CMO
CEO
CRO
Each of these probably has 3 types within them